## Sheet1
[9 empty] | Josiah | Anderson | Daniel | Alex
Task Name: (Dependencies top to bottom) | [8 empty] | Manager | Developer | Tester QA | Developer | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 4 |  | 4
|  | Design architecture | Project Manager/ All | Josiah/ All | 4 |  | 4 |  | 4 |  | 4
| Requirements |  |  |  |  | 12 |  | 6 |  |  |  |  | 0
|  | Gather | Requirements team | All | 4 |  | 2 |  | 2 |  | 2
|  | Analyze | Requirements team | All | 4 |  | 2 |  | 2 |  | 2
|  | Specify | Requirements team | All | 4 |  | 2 |  | 2 |  | 2
| Documentation |  |  |  |  | 21 |  | 9 |  |  |  |  | 0
|  | Project Charter | Project Manager | Josiah | 4 |  | 3 |  | 3
|  | Release Plan | Project Manager | Daniel | 4 |  | 3 |  |  |  | 3
|  | Requirements Document | Project Manager, Requirements Engineer | Josiah | 5 |  | 3 |  | 3
|  | Test Report | Tester | Daniel | 8 |  | 0 |  |  |  | 3
Coding | [12 empty] | 0
Iteration 1: | Development |  |  |  |  | 37 |  | 34 |  |  |  |  | 0
|  | Determine technology needs | All | All | 1 |  | 3 |  | 3 |  | 0.75
|  | Research and learn new language and environment | All | All | 20 |  | 15 |  | 15 |  | 4
|  | Create Basic Pages |  | Anderson/Alex | 8 |  | 8 |  | 8
|  | Create Basic Site Navigation |  | Anderson | 8 |  | 8 |  | 8 | 8
| Analysis |  |  |  |  | 12 |  | 2 |  |  |  |  | 0
|  | System Testing | Tester | Daniel | 4 |  | 0 |  |  |  | 0
|  | Bug fix as required | Tester, Developer | Daniel | 4 |  | 0 |  |  |  | 0
|  | Evaluate needs for next iteration | Project Manager | Josiah | 4 |  | 2 |  | 2
Iteration 2: | Design | [11 empty] | 0
|  | Design UI (CSS) | Developer | Daniel,Anderson,Alex | 2 |  |  |  |  | 2 | 2 | 2
| Development | [11 empty] | 0
|  | Review requirements | Developer | Daniel,Anderson,Alex | 1 |  | 1 |  |  | 1 | 1 | 1
|  | Wix widgets | Developer | Daniel,Anderson,Alex | 1 |  | 1 |  |  | 1 | 1 | 1
|  | Create pages as required | Developer | Daniel,Anderson,Alex | 1 |  | 1 |  |  | 1 | 1 | 1
| Analysis | [11 empty] | 0
|  | System Testing | Tester | Daniel | 2 |  | 0 |  |  |  | 0
|  | Bug fix as required | Tester, Developer | Daniel | 2 |  | 0 |  |  |  | 0
|  | Evaluate needs for next iteration | Project Manager | Josiah | 2 |  | 2 |  |  |  | 2
Iteration 3: | Design | [11 empty] | 0
| Development | [11 empty] | 0
| Analysis | [11 empty] | 0
Total

## Example
Task Name: (Dependencies top to bottom) | [8 empty] | David | Casey | Cuong | Kyle | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 2
|  | Design architecture | Project Manager | David, Casey | 12 |  | 2 |  | 2 | 0 |  |  | 2
| Requirements |  |  |  |  | 9 |  | 9 |  |  |  |  | 0
|  | Gather | Requirements Engineer | David, Casey | 2 |  | 3 |  | 2 | 1 |  |  | 3
|  | Analyze | Requirements Engineer | David, Casey | 4 |  | 3 |  | 2 | 1 |  |  | 3
|  | Specify | Requirements Engineer | David, Casey | 3 |  | 3 |  | 1 | 2 |  |  | 3
| Documentation |  |  |  |  | 28 |  | 38.5 |  |  |  |  | 0
|  | Project Charter | Project Manager | Casey, David | 2 |  | 3 |  | 0 | 3 |  |  | 3
|  | Release Plan | Project Manager | David, Casey | 2 |  | 3.5 |  | 0.5 | 3 |  |  | 3.5
|  | Requirements Document | Project Manager, Requirements Engineer | Casey, David | 5 |  | 6.5 |  | 0.5 | 6 |  |  | 6.5
|  | Project Plan | Project Manager, Developers | Casey, David, Kyle, Cuong | 5 |  | 8 |  | 0 | 6 |  | 2 | 8
|  | Architecture Document | Architect | David, Casey | 4 |  | 4 |  | 2 | 2 |  |  | 4
|  | Test Report | Tester | Casey, David | 8 |  | 7 |  | 1 | 6 |  |  | 7
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Casey, David, Kyle, Cuong | 2 |  | 6.5 |  | 0.5 | 5 |  | 1 | 6.5
Coding | [6 empty] | 0 | [5 empty] | 0
Iteration 1: | Development |  |  |  |  | 61 |  | 78 |  |  |  |  | 0
|  | Determine technology needs | Developer | Kyle, Cuong | 1 |  | 2 |  |  |  | 1 | 1 | 2
|  | Research and learn new language and environment | Developer | Kyle, Cuong | 20 |  | 32 |  | 1 |  | 22 | 9 | 32
|  | Set up proxy server software | Developer | Kyle, Cuong | 8 |  | 5 |  | 5 |  |  |  | 5
|  | Write basic proxy code | Developer | Kyle, Cuong | 5 |  | 10 |  | 10 |  |  |  | 10
|  | Implement classes | Developer | Kyle, Cuong | 10 |  | 12 |  |  |  |  | 12 | 12
|  | Create HTTP handling code | Developer | Kyle, Cuong | 8 |  | 5 |  |  |  |  | 5 | 5
|  | Write code to store user name locally | Developer | Kyle, Cuong | 2 |  | 8 |  |  |  |  | 8 | 8
|  | Write code for managing HTTP session | Developer | Kyle, Cuong | 5 |  | 4 |  |  |  |  | 4 | 4
|  | Unit Testing | Developer | Kyle, Cuong | 2 |  | 0 | [5 empty] | 0
| Analysis |  |  |  |  | 6 |  | 5 |  |  |  |  | 0
|  | System Testing | Tester | Casey, David | 2 |  | 2 |  | 1 | 1 |  |  | 2
|  | Bug fix as required | Tester, Developer | David, Casey, Kyle, Cuong | 2 |  | 1 |  |  |  |  | 1 | 1
|  | Evaluate needs for next iteration | Project Manager | David, Casey | 2 |  | 2 |  | 1 | 1 |  |  | 2
Iteration 2: | Design |  |  |  |  | 12 |  | 3.6 |  |  |  |  | 0
|  | Implement any design changes | Project Manager | David, Casey | 2 |  | 0.5 |  | 0.5 |  |  |  | 0.5
|  | Risk analysis | Project Manager | Casey, David | 2 |  | 1 |  | 0.5 | 0.5 |  |  | 1
|  | Design XML format | Developer | Cuong, Kyle | 1 |  | 0.1 |  |  |  |  | 0.1 | 0.1
|  | Design Perl XML-handling code | Developer | Cuong, Kyle | 5 |  | 0 | [5 empty] | 0
|  | Create UI design for balance screen | Developer | Cuong, Kyle | 2 |  | 2 |  |  |  |  | 2 | 2
| Development |  |  |  |  | 22 |  | 30 |  |  |  |  | 0
|  | Review requirements | Developer | Cuong, Kyle | 1 |  | 1.5 |  |  |  | 0.5 | 1 | 1.5
|  | Create XML parsing code | Developer | Cuong, Kyle | 5 |  | 3.5 |  |  |  | 3.5 |  | 3.5
|  | Handle XML data structure for retrieving balance | Developer | Cuong, Kyle | 10 |  | 15 |  | 3 |  | 12 |  | 15
|  | Implement UI | Developer | Cuong, Kyle | 4 |  | 8 |  |  |  | 2 | 6 | 8
|  | Unit Testing | Developer | Cuong, Kyle | 2 |  | 2 |  |  |  | 2 |  | 2
| Analysis |  |  |  |  | 6 |  | 5.5 |  |  |  |  | 0
|  | System Testing | Tester | Casey, David | 2 |  | 1.5 |  | 0.5 | 1 |  |  | 1.5
|  | Bug fix as required | Tester, Developer | David, Casey, Kyle, Cuong | 2 |  | 3.5 |  | 0.5 |  | 2 | 1 | 3.5
|  | Evaluate needs for next iteration | Project Manager | David, Casey | 2 |  | 0.5 |  | 0.5 |  |  |  | 0.5
Iteration 3: | Design |  |  |  |  | 22 |  | 7.5 |  |  |  |  | 0
|  | Implement any design changes | Project Manager | David, Casey | 2 |  | 0.5 |  | 0.5 |  |  |  | 0.5
|  | Risk analysis | Project Manager | Casey, David | 2 |  | 1 |  | 0.5 | 0.5 |  |  | 1
|  | Create UI design for vendor locations | Developer | Kyle, Cuong | 10 |  | 4 |  | 1 |  |  | 3 | 4
|  | Design data structure for RSS location list | Developer | Kyle, Cuong | 8 |  | 2 |  | 2 |  |  |  | 2
| Development |  |  |  |  | 29 |  | 5 |  |  |  |  | 0
|  | Review requirements | Developer | Kyle, Cuong | 1 |  | 0 | [5 empty] | 0
|  | Develop code for processing vendor locations | Developer | Cuong, Kyle | 10 |  | 3 |  |  |  |  | 3 | 3
|  | Implement vendor map display | Developer | Kyle, Cuong | 8 |  | 0 |  |  |  |  | N/A | 0
|  | Display vendor information | Developer | Kyle, Cuong | 8 |  | 2 |  |  |  |  | 2 | 2
|  | Unit Testing | Developer | Kyle, Cuong | 2 |  | 0 | [5 empty] | 0
| Analysis |  |  |  |  | 5 |  | 2.1 |  |  |  |  | 0
|  | Acceptance Testing | Tester, Project Manager | David, Casey | 3 |  | 1.5 |  | 1 | 0.5 |  |  | 1.5
|  | Bug fix as required | Tester, Developer | David, Casey, Kyle, Cuong | 2 |  | 0.6 |  | 0.5 |  |  | 0.1 | 0.6
Total |  |  |  |  | 212 | 212 | 186.2 | 186.2 | 40.5 | 39.5 | 45 | 61.2 | 186.2